## Sheet1
Week 1 | June 19 - 24
| M | T | W | TR | F | S
Milestone | Repo + Branches |  |  |  | VISUAL DESIGN LOCK | WTF CHARACTER | Know whether to have a freelancer by now
Chris | Create GitHub Repo
Kenny | Join Repo & Clone | Visual Re-Design Exploration
Ethan | Join Repo & Clone |  |  |  |  | Research GIF techniques
Week 2 | June 26 - July 1
| M | T | W | TR | F | S
Milestone | Create Branch for Mechanics Exploration |  | Playtest Version |  | MECHANIC DESIGN LOCK | Character Rig / Anims begun
Chris | New Mechanics Exploration
Kenny | Clone Repo | Create UI / 2D Deliverables + Main Menu, (Options) Design
Ethan | Sound Design Exploration |  |  | Find Background Music Track(s)
Week 3 | July 3 - 8
| M | T | W | TR | F | S
Milestone |  | PLAYTEST |  | PLAYTEST | PLAYTEST | Character finished + #Screenshot Saturday
Chris | New Mechanics Coding
Kenny | Level Design + Menu Design
Ethan | Process Sound Design |  |  | Implement Sound Design
Week 4 | July 10 - 15
| M | T | W | TR | F | S
Milestone |  |  | CONTENT COMPLETE + PLAYTEST | PLAYTEST | LOCK BUILD | #Screenshot Saturday | Come to Blossom St. on TR, F
Chris | Polish Code / QoL Fixes |  | Bugfix |  |  |  | QoL = scene transitions, defaults, etc.
Kenny | Implement UI |  |  | Polish Art Assets / UI
Ethan | Post-Processing / Color Pass |  |  | Marketing Materials / Page Design
Week 5 | July 17 - 22
| M | T | W | TR | F | S
Milestone |  |  |  | Rough Launch Page | LAUNCH | Archive all Documents, Builds
Chris
Kenny | Marketing Materials / Page Design
Ethan | Marketing Materials | Itch.io Page Design | Social Media Copy | Launch Page | LAUNCH