## Sheet1
Week 1 | June 19 - 24 |  |  |  | 23 | 24
| M | T | W | TR | F | S
Milestone | Repo + Branches |  |  |  | VISUAL DESIGN LOCK | WTF CHARACTER | Know whether to have a freelancer by now
Chris | Create GitHub Repo
Kenny | Join Repo & Clone | Visual Re-Design Exploration
Ethan | Join Repo & Clone |  |  |  |  | Research GIF techniques
Week 2 | June 26 - July 1 |  |  |  | 30 | 1
| M | T | W | TR | F | S
Milestone |  |  |  |  | MECHANIC DESIGN LOCK | Character Rig / Anims begun
Chris | New Mechanics Exploration
Kenny | Clone Repo | Create UI / 2D Deliverables + Main Menu, (Options) Design
Ethan | Sound Design Exploration
Week 3 | July 3 - 8
| M | T | W | TR | F | S
Milestone | [6 empty] | Wtf are we doing about animations
Chris | Chris Blew Up His Hand
Kenny | Kenny on Vacation
Ethan |  |  |  |  | Finish Music, Further Sound Design
Week 4 | July 10 - 15 |  |  |  | 14 | 15
| M | T | W | TR | F | S
Milestone |  |  |  |  | PLAYTEST | #Screenshot Saturday + PLAYTEST
Chris | Updating Old Code
Kenny | Level Design
Ethan |  |  |  |  | Implement Sound Design
Week 5 | July 17 - 22 |  |  |  | 21 | 22
| M | T | W | TR | F | S
Milestone |  |  |  |  | PLAYTEST | #Screenshot Saturday + PLAYTEST | Come to Blossom St. on F, S
Chris | New Mechanics Coding |  |  | Implementing UI, Polish
Kenny | Finish Level Design |  |  | Polish UI Assets
Ethan | [5 empty] | Marketing Research
Week 6 | July 24 - 29 |  | 26 | 27 | 28th
| M | T | W | TR | F | S
Milestone |  |  | CONTENT COMPLETE + PLAYTEST | Rough Launch Page + FINAL PLAYTEST + LOCK BUILD | LAUNCH | Archive all Documents, Builds
Chris | QoL + Bugfixing
Kenny | Final Level Design |  | Marketing Materials / Page Design
Ethan | Post-Processing / Color Pass | Itch.io Page Design | Social Media Copy | Launch Page | LAUNCH | Archive all Documents, Builds